## Sheet1
Haramaya University
Africa Center of Excellence (ACE)
| for Climate Smart Agricultre and Biodiversity Concervation (Climate SABC) | [5 empty] | Year 2019/20
Activity No. | Activity | Objective | Justifications | Outputs | Estimated Budget | Responsible unit | July 2019 - June, 2020
[7 empty] | July-19 | Aug-19 | Sept-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Remarks
Action plan 1: Achieving excellence in teaching-learning
1.1 | Announce and screen new MSc and PhD Students | to select top scorers; encourage female students; and balance national and regional students | to meet project's and center's targets | admission of capable students in both programs | 4000 | ACE CAES PGPD | X
1.2 | Pay stipends to enrolled students | to cover costs of living of the students | to attract regional and female national students | 10 PhD and 25 MSc students to be enrolled during the budget year in addition to students in first and second cohort | 190000 | ACE Finance, Head training & Research, and Finance Administration Directorate | X | X | X | X | X | X | X | X | X | X | X | X
1.3 | Invite visiting scholars from different institutions (regional and international) to handle course and share experience | to ensure relevance and quality of education | lack of faculty in the country in certain specializations | Effective course delivery and well-organized learning matrials | 100000 | Head, Training & Research, Graduate Council, ACE Project Manager |  |  |  | X | X | X | X | X | X | X | X | X
1.4 | Invite visiting scholars from different national institutions to handle course and share experience | to ensure relevance and quality of education | lack of faculty in the university in certain specialization | Effective course delivery and well-organized learning materials | 25000 | Head, Training & Research, Graduate Council, ACE Project Manager |  |  |  | X | X | X | X | X | X | X | X | X
1.5 | Invite faculty members of the university to handle courses | to ensure relevance and quality of education | lack of permant teachin staff at ACE Climate SABC | Effective course delivery and well-organized learning matrials | 20000 | Head, Training & Research, Graduate Council, ACE Project Manager |  |  |  | X | X | X | X | X | X | X | X | X
1.6 | Organize educational trips for students | to make students have practical exposure to smallholder farmers' climate change adaptation and agro-biodiversity conservation practices | to strengthen the student learning on campus with practical exposure | Enhanced awareness on indigenous knowledge and practices | 15000 | Course instructors; Head Training & Research, and Project Manager | [8 empty] | X
1.7 | Conduct assertiveness training for females faculty and students | to empower female students and faculty affliated to the Center | the need to develop more female leaders | Assertive female leaders | 10000 | Training & Research Head, project Manager, Gender Directorate |  |  |  | X
1.8 | Conduct envionmental and social safegaurd training | to enhance awareness and develop practical skills for creating greener and socially condusive environment | Low level of awareness and limitted skills for ensuring environment and the social sustainability | Enhanced enviromental and social sensitivity and practical skills | 8000 | Environmental and social safeguard officer at the ACE Climate SABC | X
1.9 | Conduct scientific writing and communication skills training | to enhance scientific writing and communication skills of postgraduate students | Limited scientific writing and communication skills | Enhanced scientific writing and communication skills | 7000 | Head, Training & Research at ACE and Project Manager |  |  |  | X | [6 empty] | X
1.1 | Conduct data management and software application (Stata) training | to enhance research skills of postgraduate students | Limited data management and software application skills | Enhanced data management and software application skills | 10000 | ACE Management |  | X
1.11 | Conduct GHG emission measurement and mitigation training | to develop practical research skills and knowledge of postgraduate students | Limited GHG emission measurement skills and mitigation strategies | Enhanced GHG emission measurement skills and knowledge on mitigation strategies | 5000 | ACE Management | [8 empty] | X
1.12 | Support participation of ACE staff in soft-skill enhancement short courses | to ensure effective delivery of services | Limited soft-skills of the ACE staff | Enhanced soft-skills | 15000 | Head Training & Research and Project Manager | [12 empty] | Implemented when opportunties are available
1.13 | Support paricipation of ACE affliated faculty on short courses and/or knowledge sharing events | to enhance human resource capacity of the institution | Lack of funding for participation in such event; need for incentivize affiliated faculty member | Enhanced capacity and networking with scientific community | 15000 | Head Training & Research and Project Manager | [12 empty] | Implemented when opportunties are available
1.14 | Support participation of ACE students on short course/knowledge sharing events | to enhance the capacity of the postgraduate students | lack of funding and knowledge gap of the postgraduate students in the areas the center can't address | Enhanced capacity and networking with scientific community | 10000 | Head Training & Research and Project Manager | [12 empty] | Implemented when opportunties are available
Total budget to enhace learning excellence |  |  |  |  | 434000
Action Plan 2: Program review and accreditation
2.1 | Undertake internal review of programs; obtain feedback from external reviewers; organize review workshop; documenting the reveiwed programs | to improve relevance and quality of the programs | Continuous improvement of the programs | Relevant and quality programs | 20000 | ACE Leaders |  |  | X
2.2 | Refurbish and upgrade ICT infrustructure, services, and class/conference rooms | to support learning and research with ICT | Limitation of the existing ICT infrastructure and Services | Efficient and effective ICT Services | 25000 | ICT directorate; Project Manager; Training & Research Head |  |  | X |  |  | X |  |  | X |  |  | X
2.3 | Purchase of software and e-resources | to improve relevance and quality of the programs | Overcome shortage of latest materials and software for effective data management | Availability of software and e-resouces at the Center | 5000 | Project Manager | [5 empty] | X
2.4 | Complete installation of video conferencing facilities | to create a virtual learning platform at the center; to facilitate communication | Provide quality education by distinguished scholars for world class institutions through the use of the platform | Fuctional video conferencing facilities | 260000 | ICT directorate; Project Manager; Training & Research Head | X | X | X
2.5 | Conduct benchmarking exercise | to ensure continuous improvement of ACE Climate SABC | Support the emerging Center improve over time | Assessment report and recommendations for improvements | 15000 | ACE Leaders | [12 empty] | Conducted when announced by PASET
2.6 | Obtain regional accreditation | to ensure quality and relevance of the the programs run at the center | promote the center as a competent (certified) Center of Excellence regionally. | Regional certification | 25000 | ACE leaders |  |  |  | X | X | X
Total for review and accreditation |  |  |  |  | 350000
Action plan 3: Promoting and integrating national, regional and international parterships
3.1 | Initiate partership with national private sector | to conduct collaborative research, to promote staff and student exchange | Promote university-industy linkage, achieve the overall objective of the Center, additional resource mobilzation | Joint project with pooled resources, Context-relevant curricula, practical exposure for students | 10000 | ACE leaders | X | X | X | X | X | X | X | X | X | X | X | X
3.2 | Initiate partnership with national, regional and international institutions/civil societies for collaboration | to conduct collaborative research, to promote staff and student exchange | Enable capacities and capabilities sharing | Joint project with pooled resources, curricula with international flavor, exposure to better practices elsewhere | 15000 | ACE Leaders | X | X | X | X | X | X | X | X | X | X | X | X
Total budget for partnership |  |  |  |  | 25000
Action plan 4: Enhancing and achieving research excellence
4.1 | Short-term training on lab management for techinical assistants | to improve laboraty services for researchers | limitation on skills of lab management | Enhanced skills and motivation of the technical assistants | 10000 | ACE project team | [7 empty] | X
4.2 | Refurbish lab equipement, chemicals and reagents | to enable students and faculty affiliated to the ACE conduct cutting-edge research | Generate new technology, knowledge, and policy relavant evidences as inputs for achieving climate smart agriculture and sustainable biodiversity management | Functional and state of the art laboratory facilities | 100000 | Laboratory management directorate; Dean, CAES; Project Manager; Training and Research Head at ACE |  |  |  | X | X | X
4.3 | Review PhD and MSc Research Proposals | to ensure quality of the research proposals | rigorous review as a mechanism for ensuring quality | revised proposals fulfilling the required standards | 15000 | Training and Research Head and affliated faculty | X | X | X | X | X | X | X | X | X | X | X | X
4.4 | Supervise students' research projects | to provide techincal backstopping to regional students while on research in their respective countries | ensure research quality | quality and publishable research output | 25000 | Student research advisors & Training and Research Head | X | X | X | X | X | X | X | X | X | X | X | X
4.5 | Provide research grants to postgraduate students | to the cover the research costs | lack of alternative funding source/s | achieve project targets | 197000 | ACE management | X | X | X | X | X | X | X | X | X | X | X | X
4.6 | Cover supervision fees (honorarium) | to provide quality guidance by qualified scholars to postgraduate students | Postgraduate research needs quality guidance | achieve project targets | 16565 | ACE management | X | X | X | X | X | X | X | X | X | X | X | X
| Total budget for research excellence |  |  |  | 363565
Action plan 5: Management and governance
5.1 | Run the project activities | to ensure smooth implementation of day-to-day activities of the Center | need for effective operation of the Center | Well-functioning Center | 103488 | ACE Project team | X | X | X | X | X | X | X | X | X | X | X | X
5.2 | Convene and attend National Steering Committee meetings | to review ACEs progress and provide guidance for future operations | need for adresssing emerging challenges and sharing experiences | achieve project targets | 2700 | ACE leaders | [5 empty] | X
5.3 | Convene and attend Regional Steering Committee meetings | to review ACEs progress and provide guidance for future operations | need for adresssing emerging challenges and sharing experiences | achieve project targets | 7140 | IUCEA |  |  |  |  | X | [5 empty] | X
5.4 | Develop Center policies and guidelines | to ensure transparency, fairness and efficiency in the project management | need for policies and guidelines that take into account the uniquiness of the Center as well as the need to meet the requiremnets of the World Bank | achieve project targets and compliance the bank's requirements | 2500 | ACE Project Manager |  |  | X | [5 empty] | X
5.5 | Promote and advertise the center | to ensure the visibility of the center at national, regional and internation levels | need for enhancing netwroking, partnership, and recognition of the Center and the university | achieve recognition as Center of Excellence in the continent | 5000 | ACE Comminication Officer | X | X | X | X | X | X | X | X | X | X | X | X
5.6 | Conduct internal and extrnal audits | to ensure transparency and efficiency in the untilization of project finance | need for establishing accountability | Efficient use of project finance | 3570 | ACE Project Manager |  | X | X
Total budget for management and governance |  |  |  |  | 124398
Action plan 6: Achieving sustanable financing
6.1 | Develop grant-winning proposals with local, regional and international partners | to provide supports to affiliated faculty for networking proposal writing | need to generate additional resources to sustain the research and training activitiies at the Center | Grants from exterenal sources | 10500 | ACE project team | X | X | X | X | X | X | X | X | X | X | X | X
6.3 | Attract more self-sponsoring and those students obtained scholarship fund from other third party sources | to secure alternatives funding sources | need to sustain the program through diversified funding sources | Self-sponsored and third party scholarship granted students | 5000 | ACE leaders, ACE Project team and affiliated faculty | X | X | X | [7 empty] | X
Total budget for sustainable financing |  |  |  |  | 15500
Grand total |  |  |  |  | 1312463