## Sheet1
Haramaya Universi+G4+A1:Y42
Africa Center of Excellence (ACE)
for Climate Smart Agriculture and Biodiversity Conservation (Climate SABC)
Activity No. | Activity | Objective | Justifications | Outputs | Estimated Budget | Responsible unit | July 2020 - June, 2021
[7 empty] | July-21 | Aug-21 | Sept-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22 | Apr-22 | May-22 | Jun-22 | Remarks
Action plan 1: Achieving learning excellence
1.1 | Announce and screen new MSc and PhD Students | to select top scorers; encourage female students; and balance national and regional students | to meet center's targets and ensure sustainability | admission of capable students in both programs | 4000 | ACE CAES PGPD |  | X | X | x
1.2 | Pay stipends to enrolled students | to cover costs of living of the students | to attract regional and female national students | For PhD and MSc students (1st to 4th Cohorts) | 121080 | ACE Finance, Head training & Research, and Finance Administration Directorate | X | X | X | X | X | X | X | X | X | X | X | X
1.3 | Invite visiting scholars from different institutions (regional and international) to handle course and share experience | to ensure relevance and quality of education | lack of faculty in the country in certain specializations | Effective course delivery and well-organized learning martials | 10000 | Head, Training & Research, Graduate Council, ACE Project Manager |  |  |  | X | X | X | X | X | X | X | X | X | additional $10,000 to be covered from other sources
1.4 | Invite visiting scholars from different national institutions to handle course and share experience | to ensure relevance and quality of education | lack of faculty in the university in certain specialization | Effective course delivery and well-organized learning materials | 15000 | Head, Training & Research, Graduate Council, ACE Project Manager |  |  |  | X | X | X | X | X | X | X | X | X | additional $15,000 to be covered from other sources
1.5 | Invite faculty members of the university to handle courses | to ensure relevance and quality of education | lack of permanent teaching staff at ACE Climate SABC | Effective course delivery and well-organized learning materials | 15000 | Head, Training & Research, Graduate Council, ACE Project Manager |  |  |  | X | X | X | X | X | X | X | X | X | additional $15,000 to be covered from other sources
1.6 | Organize educational trips for students | to make students have practical exposure to smallholder farmers' climate change adaptation and agro-biodiversity conservation practices | to strengthen the student learning on campus with practical exposure | Enhanced awareness on indigenous knowledge and practices | 10000 | Course instructors; Head Training & Research, and Project Manager |  |  |  | X |  |  |  |  | X
1.7 | Assertiveness training for females faculty and students | to empower female students and faculty affiliated to the Center | the need to develop more female leaders | Assertive female leaders | 15000 | Training & Research Head, project Manager, Gender Directorate | [5 empty] | X
1.8 | Innovative teaching methods training for academic staff | to equip academic staff with innovative teaching methods | limited skills in innovative teaching methods | Enhance learning excellence | 15000 | Training & Research Head and Project Manager | [10 empty] | X
1.9 | Support participation of ACE affiliated faculty on short courses and/or knowledge sharing events | to enhance human resource capacity of the institution | Lack of funding for participation in such event; need for incentivize affiliated faculty member | Enhanced capacity and networking with scientific community | 18600 | Head Training & Research and Project Manager |  |  |  | X | X | X | X | X | X | X | X | X | Implemented when opportunities are available
1.1 | Purchase of office supplies and machines (like computers) | to smoothen the operation of the Center | Limited material resources | Efficient operation of the Center's activities | 30000 | Procurement and Property administration officer | X | X | X |  |  | X
1.11 | Support participation of ACE students on short course/knowledge sharing events | to enhance the capacity of the postgraduate students | lack of funding and knowledge gap of the postgraduate students in the areas the center can't address | Enhanced capacity and networking with scientific community | 10000 | Head Training & Research and Project Manager |  |  |  | X | X | X | X | X | X | X | X | X | Implemented when opportunities are available
1.12 | Undertake curricula review workshop | to improve relevance and quality of the programs | Continuous improvement of the programs | Relevant and quality programs | 30000 | ACE Leaders | [10 empty] | X
Total budget to enhance learning excellence |  |  |  |  | 293680
Action plan 2: Promoting and integrating national, regional and international partnerships
2.1 | Initiate partnership with national private sector and to plan and implement joint project | to conduct collaborative research, to promote staff and student exchange | Promote university-industry linkage, achieve the overall objective of the Center, additional resource mobilization | Joint project with pooled resources, Context-relevant curricula, practical exposure for students | 12000 | ACE leaders | X | X | X | X | X | X | X | X | X | X | X | X
2.2 | Initiate partnership with national, regional and international institutions/civil societies for collaboration and to plan and implement joint projects | to conduct collaborative research, to promote staff and student exchange | Enable capacities and capabilities sharing | Joint project with pooled resources, curricula with international flavor, exposure to better practices elsewhere | 12000 | ACE Leaders | X | X | X | X | X | X | X | X | X | X | X | X
Total budget for partnership |  |  |  |  | 24000
Action plan 3: Enhancing and achieving research excellence
3.1 | Lab management training for technical assistants | to improve laboratory services for researchers at own and emerging universities | limitation on skills of lab management | Enhanced skills and motivation of the lab assistants at own and emerging Universities | 10000 | ACE project team, Laboratory Management Directorate |  |  |  |  | x
3.2 | Postgraduate supervision training for university staff | to develop practical research skills and knowledge of postgraduate students | Limited skills of advisors on effective ways of guiding students while conducting research | Enhanced advisors capacity for better guidance of students research | 15000 | ACE Management | [10 empty] | X
3.3 | Research methods and Data Analysis Software training for academic staff | to enhance research skills of postgraduate students | Limited research skills of the staff | Enhanced research capabilities, skills and application of software | 15000 | ACE Management | [10 empty] | X
3.4 | Integrated Decision Support System Training in collaboration with Texas A & M and Florida University | to enhance research skills of postgraduate students | Limited data management and software application skills | Enhanced data management and software application skills | 5000 | ACE Management | [6 empty] | X | [5 empty] | implementation depend on the availability of the trainer
3.5 | Research Methods and Scientific Writing training | to enhance scientific writing and communication skills of postgraduate students of own University and junior staff of emerging universities | Limited scientific writing and communication skills | Enhanced scientific writing and communication skills | 7500 | Head, Training & Research at ACE and Project Manager |  |  | X | [7 empty] | X
3.6 | Review PhD and MSc Research Proposals | to ensure quality of the research proposals | rigorous review as a mechanism for ensuring quality | revised proposals fulfilling the required standards | 5000 | Training and Research Head and affiliated faculty | X | X | X | X | X | X | X | X | X | X | X | X
3.7 | Provide research grants to postgraduate students | to the cover the research costs | lack of alternative funding source/s | achieve project targets | 166400 | ACE management | X | X | X | X | X | X | X | X | X | X | X | X
3.8 | MSc/PhD thesis/dissertation examination and cover supervision fees (honorarium) | to provide quality guidance by qualified scholars to postgraduate students | Postgraduate research needs quality guidance | achieve project targets | 77000 | ACE management |  |  |  | X |  |  | X |  |  |  | X
3.9 | organize international conference | to disseminate research outputs for enhanced knowledge sharing and networking | limited means of dissemination of research outputs and knowledge | enhanced dissemination of research outputs | 25000 | Training and Research Head and Project Manager | [8 empty] | X
3.1 | Develop policy briefs and produce conference proceeding | to ensure transparency, fairness and efficiency in the project management | need for policies and guidelines that take into account the uniqueness of the Center as well as the need to meet the requirements of the World Bank | achieve project targets and compliance the bank's requirements | 5000 | ACE Project Manager |  |  |  |  | X |  |  |  |  | X
3.11 | Covering publications costs for students | to promote high quality publications | limited budget for publications of scientific articles | Enhanced visibility research outputs | 4000 | ACE Management | X | X | X | X | X | X | X | X | X | X | X | X
3.12 | Conduct onsite research progress monitoring | to promote research quality | low research quality and progress delay | Enhance quality and completion rate | 10000 | ACE Management | X | X | X | X | X | X | X | X | X | X | X | X
| Total budget for research excellence |  |  |  | 344900
Action plan 4: Management and governance
4.1 | Running project activities | to ensure smooth implementation of day-to-day activities of the Center | Payment of staff salaries and vehicle operation costs for effective operation of the Center | Well-functioning Center | 175000 | ACE Project team | X | X | X | X | X | X | X | X | X | X | X | X
4.2 | Support participation of ACE staff in soft-skill enhancement short courses | to ensure effective delivery of services | Limited soft-skills of the ACE staff | Enhanced soft-skills | 10000 | Head Training & Research and Project Manager | X | X | X | X | X | X | X | X | X | X | X | X | Implemented when opportunities are available
4.3 | Support training on leadership and Change Management for University staff | to ensure effective leadership at the University and Center Level | Need for effective leadership at all levels | Well-functioning University and Center | 10000 | ACE Leaders | X | X | X | X | X | X | X | X | X | X | X | X
4.4 | Convene and attend National Steering Committee meetings | to review ACEs progress and provide guidance for future operations | need for addressing emerging challenges and sharing experiences | achieve project targets | 5000 | ACE leaders |  |  |  | X |  |  |  | X |  |  |  | X
4.5 | Convene and attend Regional Steering Committee meetings | to review ACEs progress and provide guidance for future operations | need for addressing emerging challenges and sharing experiences | achieve project targets | 7500 | IUCEA |  |  |  |  | X | [5 empty] | X
4.6 | Promote and advertise the Center | to ensure the visibility of the center at national, regional and international levels | need for enhancing networking, partnership, and recognition of the Center and the university | achieve recognition as Center of Excellence in the continent | 5000 | ACE Communication Officer | X | X | X | X | X | X | X | X | X | X | X | X
4.7 | Conduct internal and external audits | to ensure transparency and efficiency in the utilization of project finance | need for establishing accountability | Efficient use of project finance | 7500 | ACE Project Manager, ACE Audit Committee |  | X | X | X | X
Total budget for management and governance |  |  |  |  | 220000
Action plan 5: Achieving sustainable financing
5.1 | Develop grant-winning proposals with local, regional and international partners | to provide supports to affiliated faculty for networking proposal writing | need to generate additional resources to sustain the research and training activities at the Center | Grants from external sources | 10000 | ACE project team | X | X | X | X | X | X | X | X | X | X | X | X | Any time relevant calls are available
Total budget for sustainable financing |  |  |  |  | 10000
Grand total |  |  |  |  | 892580